## Slide 1
Dr. Sylvia CC Mkandawire
Project Manager
ACE Impact Project,
Regional Facilitating Unit
Association of African Universities
ACE Impact Progress and Update
9th November 2021

## Slide 2: Presentation Focus
Overall Project Updates
Key highlight for 1st and 2nd ACE Impact countries
Areas of Significant Progress
Challenges

## Slide 3
PROJECT ACHIEVEMENTS HIGHLIGHTS
January 2019 – September 2021
14,761 Students (59%)
2,020 PhD Students (84%)
6,443 MSc Students (77%)
US$58,530,369 Revenue (98%)
6,298 PSTC Students (44%)
3,506 Regional Students (49%)
4,585 Female Students (55%)
2,282 Internships (48%)
2,129 Publications (89%)
Significant Progress

## Slide 4
Areas of Significant Progress
3
4
5
6
1
2
Achievements
31% DLIs achieved
Innovations
Centers contributions to fight against covid thru Research & Technological innovations
Digital Transformation
Digital learning and infrastructure initiative to provide digital education coaching to support centres become competent in digital education
Partnerships
EPFL, IBM, PARTNER, WB, Elsevier, US-NIH
Operations
Successful AWP, Procurement plans, Core Teams in Place
Collaboration
Centres linked with WB Global Practice Projects at national and regional scope

## Slide 5: Summary of Key Observations
  FIRST ACE IMPACT
  DLIs on Track; 3/5 Project Development Objectives on target; International Accreditation in Progress
  ACEs Lagging fund utilization (17.2%)
  Centres excelling in earning funds but are behind in spending;
  Average DLI Achievement Rate 42%
  Projected 100% of DLI achievement by project end.
  SECOND ACE IMPACT
  DLIs on track 2/5 Project Development Objectives on Target
  ACEs are Lagging in earnings (23%) and spending funds (6.9%)
  Expected improvement before the MTR in March 2022
  Average DLI Achievement Rate is 23%
  Projected 100% of DLI achievement at the end of the project if achievement rate is doubled & one year extension

## Slide 6
ACE IMPACT PROJECT CHALLENGES ENCOUNTERED
2
1
3
4
5
6
COVID-19 Disruptions: affected student recruitment, internship placements and staff mobility;
Although disbursement rates & DLI achievements are on track, fund utilization rates are low project wide;
Delays in Procurement processes especially in Francophone countries
The Gambia, Djibouti, Niger & Guinea (hosting emerging centres) are lagging in their implementation rates.
Delays in achieving project effectiveness in Nigeria and in the approval of the country's borrowing plan by its National Assembly;
Delays in Submission of ESMPs by centres - potential effect on completion of civil works;