## Slide 1
Mid Term Review (MTR)
Process and Parameters
9th November 2021

## Slide 2: MTR and Reallocation of “unallocated funds”
Country | Unallocated amount
First ACE Impact | 
Ghana | $2 million
Burkina Faso | $3 million
Guinea | $1 million
Djibouti | $2 million
Senegal | No unallocated funds
Second ACE Impact | 
Benin | $1.2 million
Togo | $2 million
Niger | $1 million
Nigeria | $10 million
Gambia | $1.5 million
Cote d Ivoire | €1.9 million
Transparent merit-based approach
Two-stage assessment
1. To determine the direction of the unallocated funds
2. To assess center performance relative to project and center’s goals
1. Funds will be allocated to centers meeting a high implementation performance benchmark criteria
2. In some countries, portions of the funds could be allocated to national agencies for ICT support to the universities
1. Based on centers’ implementation performance
2. Options to ensure project success and maximum center benefits
3. Consideration for the Covid crisis
Mid-term Review Rational
1. Provide guidance on reallocation of countries’ unallocated funds
2. Performance evaluation of centers at midterm based on Section 3.5 of Performance Contracts signed by centers, universities and government

## Slide 3: Approach on Funds reallocation
Approach : Based on the same principles and analysis for reallocation of “unallocated funds”
High performing Center (high implementation performance benchmark criteria)
Considered to be eligible to receive the unallocated funds
Low performing Center (very low implementation performance benchmark criteria)
Considered to have a severe implementation lag
Objective
Ensure efficient and optimum use of funds allocated to countries by project closing
Ensure no funds allocated to centers is not earned or unused by project closing
Importance of such an Approach
Avoid funds to be returned to the World Bank at project
Provide additional funds to well- performing centers to further advance key project activities
Signal HE has capacity to efficiently absorb funds
Show result-based approach works in supporting HE sector
Experience: Similar exercise undertaken in ACE I
Support centers to further advance key project activities
ACEGID: Partnership with Ministry of Health
CEFOR: Pre-commercialization project
CEA-MITIC project «Digital Saint Louis 2025 »
98% of funds were disbursed and used in ACE I

## Slide 4: Approach on Funds reallocation to Centers
Adding funds to well
performing centers
Reduction/partial cancellation
for lower performing centers
Center will be considered for additional funds as per Financing Agreement
Additional amount based on unallocated funds available
Additional amount based on center’s needs and activities
Center will prepare proposal on how additional amount will be allocated
Specific guidelines will be provided on DLIs/DLRs eligible for additional funds
Center with a high implementation performance benchmark criteria
Notice to improve implementation
By an agreed date
No significant improvement and the MTR confirms severe implementation lag
Large risk that funds will not be utilized by project closing
Even with a one-year project extension
Fund reduction will be considered as per Performance and Funding Agreement
Grant amount will be reduced by 50 percent of the uncommitted amount that is above half of the grant
Center with a severe implementation lag

## Slide 5: Approach on reallocation across DLIs
Two scenarios apply to reallocation across DLIs:
  allocation of additional funding to well-performing centers
  No additional funds allocated but strong justification to reallocate across DLIs
DLRs above targets at mid-term can be considered for increase in allocation for centers receiving additional funding.
Specific recommendations will be provided for each DLI/DLR with challenges
DLR | Description of DLR | Rationale | Recommendation
3.1 & 3.2 | PhD & Master students | Achievement above targets | Considered for additional funding
4.2 | Research publications |  | 
5.1 | Revenues generated |  | 
2.1 & 2.2 | Development Impact | Verification not yet begun | Not opened for reallocation
3.3 | Short-term students | Likely COVID-19 related delays to recruitment | 
4.1 | Program Accreditation | Likely Center Level Delays | 
7.1-7.6 | Institutional Impact | Verification not yet fully started | 
6.1-6.4 | Fiduciary | Likely Center Level Delays | Not opened for reallocation, except for Nigeria
4.3 | Infrastructure | Likely delays from processing ESMPs and COVID related construction pauses. | Considered for additional funding (Expected in year 3 & 4)
5.3 | Entrepreneurship | Centers have not begun process. | Considered for additional funding (To incentivize centers further)
5.2 | Internships | Likely Center Level Delays. | Can be reduced by 15% max (Given covid-19 impact)

## Slide 6
FOUR PERFORMANCE CRITERIA
DLI Achievement Rate
Proportion of results achieved by the center
Results achieved in dollar amount over the total amount of results targeted for each DLI
Fund Utilization Rate
Proportion of funds spent over the center’s total allocation
Implementation Performance Rate
Average of DLI Achievement Rate and the Fund Utilization Rate
Assess centers’ ability to receive more funds or be considered for a potential fund reduction
Qualitative Assessment
Ability to apply support missions' key recommendations
Over last 2 years and in Fall 2021
Assess ability to implement the project with the existing funds
METRICS FOR PERFORMANCE REVIEW
PERFORMANCE CRITERIA & METRICS
First ACE Impact
Second ACE Impact
Anticipated Project implementation performance rate at midterm ~ 40-50 % (under normal circumstances)
Project average considered is lower. Center performances are compared against project averages, given the COVID-19 context

## Slide 7: Implication of proposed approach
FIRST ACE IMPACT
SECOND ACE IMPACT
Country level implication/ recommendation notes on application of approach to be prepared for discussion with each country
National discussion to take place in after the November 2021 workshop
Update figures in December prior to regional workshop in November where: (i) Final application of recommendation to increase funds to centers for those benefitting from unallocated funds; (ii) Final warning to those with severe implementation lag
Discussions at country level for those who are at risk for fund reduction/partial cancelation will continue until Dec. 2021
Signal to center opportunity to improve implementation
The current Metrics are for information purposes to signal to centers their performance
To encourage the centers to accelerate implementation
Benchmarks will be updated following new data with updated with Dec 2021 IFRs and DLI results
Application of the updated data between Feb and March 2022
Regional workshop in March 2022
Country level notes on application of approach to be shared for discussion for each Second ACE Impact country