## Slide 1: Africa Centers of Excellence Project Financial Management
Accra, May 17 – 20, 2016

## Slide 2: Overview of the session
Project Financial Management
Disbursement Arrangements for ACE
Update on FM Action Plan
FM Related DLR
Next Steps & Action Plan
Questions & Answer Session

## Slide 3: Project Financial Management

## Slide 4: Financial Management Systems….
Project Financial Management Systems (Framework) include:
  Budgeting
  Accounting
  Internal Control *(Processes>Procedures>Approvals etc.)
  Funds Flow – Liquidity & Payments
  Financial Reporting –(meet DLR) & Financial Covenants
  Auditing – (Required for the DLR)
These systems inform the control environment in which the ACE projects are being implemented and need to be monitored periodically by the Bank and Stakeholders

## Slide 5: Key Documents For FM Issues …
Applicable to your Project:
  Financing Agreement (Loan / credit / grant agreement)
  Project Appraisal Document
  Disbursement Letter
  Project Implementation Manual (PIM)
  World Bank Disbursement Guidelines/Handbook
These documents used together provide all the information that the project requires on financial management in answering questions such as eligibility of expenditure, how much is an implementing agency entitled to, processes for documentation and reporting etc.
It absolutely important for all ACE Project Staff to read the FA, more so the Coordinator and the Accounts staff

## Slide 6: FM Issues after signing…
Loan Signing Date: The signing date is the most important date for projects and generally is most important for FM in determining issues such as eligibility of expenditure and retroactive financing, reimbursement etc.
Date the borrower (Govt) signs the loan agreement and other legal documents.
Date from which a payments made by the borrower becomes eligible for financing.
Exception would be cases where the loan includes provision for retroactive financing.
This is the beginning of the standard eligibility for financing even if the loan has not disbursed or declared effective.

## Slide 7: Disbursement Arrangements for ACE

## Slide 8: Disbursement Arrangements …??
These flow from the general policies and procedures and are project specific and outline issues such as:
  The disbursement methods for withdrawing funds
  Types of Supporting documenting required to document expenditures
  How to withdraw funds for implementation
Objective is :Ensuring funds are available in the amount and periods required to support smooth project implementation.
Source – Disbursement Letter and Disbursement Guidelines

## Slide 9: Disbursement Arrangements…
  Disbursement Methods: Generally four main methods for managing liquidity;
    Advance to designated bank accounts in US dollars ( up to six months or agreed ceiling)
    Direct Payment – to third parties
    Reimbursement of Funds
    Special Commitments – to mitigate risk of non payment
  All these options are available to your projects and the Bank encourages them to use them in managing their liquidity challenges.

## Slide 10: Outline of ACE Disbursement Arrangements.
  Initial Advance are made to qualifying ACE
  On a Half – Yearly Basis, ACEs submit IFR and EEP Spending Reports
  ACE submit Independent Verification Report
  The report form supporting documentation for processing WA
  Based on the level of achievement of DLRs , amounts are documented against advances
  Additional Advances requested for next half year
  *Each ACE to update the team

## Slide 11: Current Disbursement Status
Notes: Did every ACE got the first advance and the reimbursement of the first DLI ?

## Slide 12: Update on FM Action Plan
FM Related DLR

## Slide 13: Country Update on FM Action Plan….
Financial Management Action Plan-Seven (7) key parameter:
  Accounting Staff
  Internal Audit
  Functioning Audit Committee
  Computerized Accounting System
  IFR Submission and Quality of Reports
  External Audit Compliance
  Transparency & Disclosure in Financial Information
  *Each ACE to update the team

## Slide 14: FM Related DLR

## Slide 15: 4 FM Related DLRs…. DLI 3: Timely, Transparent and Institutionally Reviewed Financial Management
# | Description | Observation
DLR#3.1 | Timely withdrawal application supported by financial reporting for the ACE account for the period | First year: 2015
DLR#3.2 | Functioning Audit Committee under the university council | 
DLR#3.3 | Functioning internal audit unit for the university | 
DLR#3.4 | Web Transparency on Financial management (web-access to audit reports, interim financial reports, budgets and annual work plan) | 
25,000 USD per year and per DLR
2015, 2016, 2017, 2018

## Slide 16: FM Related DLRs…. DLI 3: Timely, Transparent and institutionally reviewed Financial Management
Four Disbursement Linked Results (DLR)
  DLR 3.1 – Timely withdrawal application supported by adequate financial reporting for the Participating University's (ACE) account for the period.
  Guidance Notes:
  Timely withdrawal application means submission through the appropriate government channels of a withdrawal application on or before the date in the agreed schedule. The schedule will be submission of withdrawal application every 6 months after the date of the project effectiveness. The withdrawal application must be complete with the required information regarding each of the results achieved and the required information regarding the Eligible Expenditure Program (EEP). It is expected that at a minimum half yearly Withdrawals

## Slide 17: FM Related DLRs…. DLI 3: Timely, Transparent and institutionally reviewed Financial Management Four Disbursement Linked Results (DLR)
  DLR 3.2 – Functioning Audit Committee under the Participating University's (ACE) councils.
  Guidance Notes:
  For the first withdrawal application requesting funding for this result:
    Guidelines/ Terms of Reference (ToR)s for the audit committee constituted under the governing body of the university;
    Members of the audit committee have been duly constituted
    Documentary evidence (report or minutes of meeting) that the Committee has met and discussed the audit for the University (ACE), the committee’s role in the project, and risks associated with the project.
    Subsequent Withdrawals
  Evidence (report or minutes of meeting) that the Committee has met and discussed the external audit for the ACE, any internal audit reports, and following up on issues raised to ensure management’s attention and correction.
  Note-: The Audit committee should in principle carry out an institutional review of the audits and follow up. However, the term functioning will be interpreted only regarding review of the ACE aspects of the audit work.

## Slide 18: FM Related DLRs…. DLI 3: Timely, Transparent and institutionally reviewed Financial Management Four Disbursement Linked Results (DLR)
  DLR 3.3 – Functioning Internal Audit Unit for the Participating University (ACE).
  Guidance Notes:
  For the first withdrawal application requesting funding for this result:
    Guidelines/ ToRs for the internal audit unit for the university (or college/school depending upon the structure of the university) has been formulated
    Staff members of the internal audit unit recruited and functioning
    Evidence (report or minutes of meeting) that the internal audit unit has discussed the university’s participation and responsibilities under the Africa Centers of Excellence project, the unit’s role in the project, and risks associated with the project.
    Subsequent Withdrawals
  Evidence (report or minutes of meeting) that the IAU has reviewed the ACE accounts and Internal controls systems using a risk based approach.
  Any changes or revisions to the guidelines/ToR should be included
  Note-: The Internal Audit should in principle carry out institutional reviews of the financial management of the University as a whole, however specifically for the project , the review will be limited to only that of the ACE.

## Slide 19: FM Related DLRs…. DLI 3: Timely, Transparent and institutionally reviewed Financial Management Four Disbursement Linked Results (DLR)
  DLR 3.4 – Transparency on financial management (web access to audit reports, IFRs, budgets and AWP)
  Guidance Notes: There must be a link to the institution's website or portal which is publically available.
  For the first withdrawal application requesting funding for this result:
    This will be limited to the financial reports of the specific ACE i.e. interim financial reports, approved budgets and work plans, and annual audit reports.
    Subsequent Withdrawals
  It is expected that in subsequent years, in addition to the specific ACE financial reports, the participating University should have it’s annual audited reports also publically available online in order to qualify for the DLR

## Slide 20: FM DLRs – Clarification
# | Description (Financingf Agreement) | Explication | Vérification protocol (Data source and methodology) | DLR communication to the Bank
DLR#3.1 | Timely withdrawal application supported by financial reporting for the ACE account for the period |  |  | 
DLR#3.2 | Functioning Audit Committee under the university council |  |  | 
DLR#3.3 | Functioning internal audit unit for the university |  |  | 
DLR#3.4 | Web Transparency on Financial management (web-access to audit reports, interim financial reports, budgets and annual work plan) |  |  | 

## Slide 21: Next Steps & Action Plan

## Slide 22: Next Steps & Action Plan….
ALL ACEs should aim at submitting a Withdrawal Application by end of June 2016
Steps:
  Submit the June 2016 Interim Financial Report & EEP Report to CO FMS
  Collect details of evidence of achievement of Year 2015 DLRs
  Obtain Independent Verification of the Year 2015 DLRs
  Submit evidence to the Bank (TTL) for review and clearance
  Prepare Withdrawal Application to document initial advance
  *Submission of Annual Audit Report for ACE due June 30, 2016

## Slide 23: DLR#3.1: Timely withdrawal application supported by financial reporting for the ACE account for the period
Requirement for each application | Best practices
IFR and attached documents (see Disb. Letter) (IFR bi-annual) EEP Spending Report provided by an Independent Verifier. | Ensure that an Independent Verifier is recruited. Designate a focal point who will assist the I.V to obtain all information required for verification. Designate a person responsible for the preparation of the Financial Reporting and supporting documents. Adopt a financial reporting action plan: action, responsible, deadline

## Slide 24: FM Issues during Closing …
  Project Closing Date: The date specified in the Financing Agreement (or later date established by the Bank by notice to the borrower) after which the Bank may, by notice to the borrower, terminate the borrower’s right to make withdrawals from the loan account and cancel any undisbursed balance of a loan. When is the project closing??
  Disbursement Deadline Date– The final date on which the Bank will accept applications for withdrawal (WA) from the borrower or documentation on the use of loan proceeds already advanced by the Bank. This date is established in the Disbursement Letter and is usually up to four months after the closing date.
  Grace Period – Common term used to denote the period between the closing date and the disbursement deadline date.

## Slide 25
THANK YOU
Open Discussions
Questions???