## Slide 1
Status of 1st & 2nd ACE Impact
Effectiveness, Implementation Readiness & Support
DR. SYLVIA MKANDAWIRE,
PROGRAM MANAGER, ACE IMPACT
ASSOCIATION OF AFRICAN UNIVERSITIES (AAU)
REGIONAL FACILITATING UNIT,
2nd Project Steering Committee Meeting
SEPTEMBER 23, 2019, Dakar, Senegal

## Slide 2: Presentation Outline
1st ACE IMPACT – FINANCING AGREEMENT
1st ACE IMPACT – PERFORMANCE CONTRACT
1st ACE IMPACT – ENDORSEMENT OF REGIONAL OPERATONS MANUAL
1st ACE IMPACT – LEGAL OPINION
1st ACE IMPACT – PARLIMANETARY/CABINENT/PM APPROVAL
2nd ACE IMPACT – PREPARATION STATUS
NATIONAL REVIEW COMMITTEE
INSTITUTIONAL READINESS

## Slide 3: 1st ACE IMPACT – FINANCING AGREEMENT
Good progress: All First ACE Impact countries have signed except for Ghana
Ghana is close to signing has received Cabinet and parliamentary approval

## Slide 4: 1st ACE IMPACT – Performance contract
Model developed and shared
Burkina, Ghana & Guinea’s drafts have been cleared by WB Legal Team and being finalized by the Centers and Government for signing
Djibouti and Senegal are yet to submit initial drafts to WB

## Slide 5: Legal opinions
Confirms that the signed Financing Agreement and Performance Contract :
  have been duly authorized/ratified by the governments and
  are legally binding upon the government and the universities
Issued by the Attorney General.
Status on Legal opinion for the Financing Agreement: Received for Burkina Faso and AAU; and remains for Djibouti, Ghana, Guinea and Senegal

## Slide 6: 1st ACE IMPACT – Parliamentary/ CABINET approval
This is the most critical for some countries like Ghana. However it not applicable in the other countries.
Ghana has finalized this important step and informed the WB

## Slide 7: National Review Committees
All countries have established the Committee!
RFU attended some National Review Committees (Ghana and Togo)
Critical role of the National Review Committee in moving the project forward
Changes in Minister Positions in other countries
    Great efforts made by PSC/Focal points in orientation of new leadership to quickly get them on board

## Slide 8: 2nd ACE IMPACT – Preparations
All preparations work have been completed
  ESMFs completed and disclosed in all countries and on WB website
  Fiduciary assessments completed in all countries
Technical discussions have been completed for all 2nd ACE Impact countries
  DLI allocations and PAD have been revised following comments provided
Negotiations with the WB have been scheduled for all countries and AAU from October 1st - 10th, 2019
  Formal invitations have been sent by the WB to all governments
  WB is awaiting formal confirmations from all governments

## Slide 9: 1st ACE Impact : Country level Effectiveness Conditions
Country | Financial Agreement | Performance Agreements | Endorsement of Regional Operations Manual | Legal Opinion | Parliamentary ratification | Deadline for effectiveness
Burkina Faso | Signed – May 10 | Draft cleared by legal | Received | FA Legal Opinion Obtained | N/A | Extended to October 8th, 2019
Djibouti | Signed – April 12 | To be submitted | Feedback to comments provided Sept 10th | In Progress | N/A | Extended to November 11th, 2019
Ghana | Yet to be signed | Draft sent to Legal for clearance | Received | In Progress | Notified the WB | TBC once signed
Guinea | Signed – April 12 | Draft Cleared by legal | Received | In Progress | N/A | Extended to November 11th, 2019
Senegal | Signed – July 19 | To be submitted | Received | In Progress | N/A | November 18, 2019
AAU | Signed – 14th June 19 | N/A | Completed | Legal Opinion Obtained | N/A | Effective August 20, 2019

## Slide 10: 2nd ACE Impact : Country level Technical discussions & negotiations
Country | Technical discussions | Negotiation meetings
Gambia | August 19, 2019 | Scheduled for October 2-3, 2019
Niger | August 22, 2019 | Scheduled for October 3-4, 2019
Togo | September 4, 2019 | Scheduled for October 1-2, 2019
Nigeria | August 29, 2019 | Scheduled for October 7-8, 2019
Benin | August 27, 2019 | Scheduled for October 9-10, 2019
Cote d’ lvoire | July 15-19th, 2019 | Scheduled for November, 2019
AAU | N/A | Scheduled for October 4, 2019

## Slide 11: 2nd ACE IMPACT – Next steps
Negotiations meeting have been scheduled for all countries and AAU, from October 1st -10th, 2019
  Invitations have been sent to all governments
Begin project effectiveness activities
  Signing of Financing Agreements
  Signing of Performance and Funding Agreements
  Legal Opinions
  Endorsement of Regional Operation Manual
  Country specific dated covenants (applicable to Niger)
Complete actions included in country specific Financial Management Action Plan

## Slide 12: Highlights of 1st ACE Impact : Institutional readiness
1

## Slide 13: Highlights of 2nd ACE Impact : Institutional readiness

## Slide 14: Implementation support
Regular technical support by RFU & WB
1
Thematic Experts linked and already supporting with centers to accelerate attainment of Institutional Readiness
2
  Supervision missions realized in May – June 2019 for Benin, Burkina Faso, Djibouti, Ghana, Guinea, Niger, Nigeria, Senegal & Togo
  Supervision missions planned in October 2019 – February 2020 for All new centers not visited
Presence during the National Steering Committee Meetings
3
Recruitment of a dedicated Program Manager for ACE Impact; Involvement of Technopolis and Procurement Expert for AAU
4
Digitization and Communication support for the ACE Impact
5

## Slide 15: 1st ACE Impact Priority Next Steps
 | ACTIONS | DUE DATES
1. | Countries to work proactively in attaining the requirements for ensuring effectiveness | Senegal-Nov 18 Djibouti-Nov 11 Guinea-Nov 11 Ghana-tbc Burkina-Oct 8
2. | Finalize submission and verification of DLI#1 – Institutional Readiness | Nov 30, 2019
3. | First disbursement to Centers | December 30, 2019
4. | Signing of subsidiary agreements between governments (Burkina Faso, Ghana, Senegal) and icipe and submission of related legal opinion for the PASET-RSIF | November 30, 2019
5. | Complete actions included in Country specific Financial Management Action Plan (most are 3-6 months post effectiveness) | March 2020

## Slide 16: 2nd ACE Impact Priority Next Steps
 | ACTIONS | DUE DATES
1. | Complete negotiations for all countries | Oct 1 – 10, 2019
2. | Submit project for World Bank approval | Nov. 26, 2019
3. | Countries work towards meeting effectiveness conditions. | Nov – Dec, 2019
4. | In parallel, finalize submission and verification of DLI#1 – Institutional Readiness | Nov 30, 2019
5. | Signing of subsidiary agreements between governments (Benin & Nigeria) and icipe and submission of related legal opinion for the PASET-RSIF | Dec 31, 2019
6. | Complete Country specific actions in Financial Management Action Plan (most 3-6 months post effectiveness) | Feb 28, 2020
We encourage Benin, Cote d’Ivoire and Nigeria governments and Centers to work closely
with AFD in finalizing required preparatory actions

## Slide 17
Email Us:
research@aau.org
Like Us on Facebook: ACEI
Follow Us on Twitter: The_ACEProject
Visit Our Blog:
http://blog.aau.org
Visit Our Website: www.ace.aau.org
Notes: You can safely remove this slide. This slide design was provided by SlideModel.com – You can download more templates, shapes and elements for PowerPoint from http://slidemodel.com