## Slide 1
KEY DECISIONS FROM LAST PSC MEETING HELD IN DAKAR, SENEGAL, 23RD SEPTEMBER, 2019
PRESENTED BY DR SYLVIA MKANDAWIRE, ACE IMPACT PROGRAM MANAGER
AT THE PSC MEETING
24th FEBRUARY 2020, NATIONAL UNIVERSITIES COMMISSION, ABUJA NIGERIA

## Slide 2: KEY DECISIONS FROM LAST PSC MEETING HELD IN DAKAR, SENEGAL
No | KEY DECISION | STATUS
1 | AAU to share the minutes of the virtual PSC meeting referenced in paragraph 6 above | This was concluded shared on 26th September 2019
2 | AFD and AAU will continue further discussions on any other pending implementation arrangements and incorporate the details into the operations manual | Virtual meetings undertaken between AAU and AFD to discuss the implementation of the PARTNER project and IRD engagements. Implementation plan for activities related to AAU has been agreed upon. Letters of agreement.
3 | AAU to send the workplan document to the PSC members for input | The workplan shared on 23RD February 2020
4 | PSC to endorse updated ACE Impact budget and workplan once shared by AAU | The workplan shared on 23RD February 2020 for PSC Endorsement

## Slide 3
No | KEY DECISION | STATUS
5 | AAU to update DLI 1 submission status information | DLI 1 submissions status information is updated. DLI 1 tracking file shared with centers on 13th February 2020. Individual reports on results submitted by the centers were issued between December 17th 2019 and January, 15th 2020.
6 | AAU to provide communication guidelines for DLI 1 and other results submissions | Completed Email was sent to all centers providing guidance on submission of DLI 1 on 4th October 2019. ACE Impact Project Manager and M&E Officer are focal person. Communication Protocol for the project was developed and cleared by the World Bank Team.
7 | AAU to respond to Niger on issues relating to assistance from Subject-matter experts | AAU/Bank Identified subject matter experts who are working closely with Niger. AAU provides guidance to Niger based on the requests and needs.
KEY DECISIONS FROM LAST PSC MEETING HELD IN DAKAR, SENEGAL

## Slide 4: KEY DECISIONS (CONT’D)
No | KEY DECISION | STATUS
8 | AAU to reshare the AFD Concept Note on the PARTNER project given some PSC members did not previously receive it due to technical challenges in the email list serve. | The concept note was recirculated/ shared with the PSC Members by email sent on 25th September 2019
9 | AAU to review and update PSC email distribution lists | The mailing list has been continuously reviewed Changes in PSC membership, new members are constantly added to the contact list.
10 | AAU to reshare all the meeting documents with the PSC | The meeting documents shared with PSC members during Senegal meeting on 25th September 2019
11 | AAU to provide capacity building and other technical assistance for Centre leaders (particularly in Côte d’Ivoire and Togo) | AAU intensified support to Togo (CERME, DOUNEDON) Cote d Ivoire (CEA MEM) centers to accelerate their readiness for DLI 1. Accelerator sessions and frequent interaction with the subject matter specialists. A need assessment for other additional capacity building activities have been carried out Supervision Mission in Cote d’Ivoire (28th – 29th October 2019) & Togo (23rd – 26th October,2019)

## Slide 5: KEY DECISIONS (CONT’D)
No |  | 
12 | The next joint ACE I and ACE Impact Regional Workshop and PSC meetings for both projects will be held in Abuja, Nigeria. | The decision implemented, and meeting has been organized to take place in Abuja, Nigeria from February 24-28, in collaboration with the National Universities Commission (NUC).
13 | AAU/WB to evaluate performance of subject matter experts | AAU has developed an expert’s evaluation survey which was administered prior to the Abuja Meeting on 14th February 2020 AAU and WB follow up with national focal points to check in on assignment of experts to the centres During supervision WB country team leaders check in with the ACE to obtain feedback on experts

## Slide 6: Experts' Understanding of the Centre's Goals/Compréhension de l’expert des objectifs du Centre:
Chart: 
| Excellent | Good/ Bon | Average/ Moyen | Fair/ Acceptable | Poor/ Médiocre
 | 0.758 | 0.212 | 0.0303 | 0 | 0

## Slide 7: Was the support from experts adequate?
Chart: 
| Yes, Fully / Oui, entièrement | Yes, Partially / Oui partiellement | No / Non
 | 0.9394 | 0.0606 | 0

## Slide 8: Support provided for IPs
Chart: 
| Clarity in communication | Met Expectations | Constructive feedback | Technical advice | Clarity in engagement | Time management | Appropraite reinforcements | Objectivity | Participatory engagements | Prompt feedback


 | 0.7273 | 0.6061 | 0.7273 | 0.6364 | 0.6061 | 0.6667 | 0.5 | 0.7879 | 0.7576 | 0.5455

## Slide 9: ADDITIONAL FEEDBACK
Strengths
Knowledge and experience in the thematic areas and African Higher Education
Weakness
Delayed feedback
Areas for Improvement
Timely feedback from experts
Proactive and detail-oriented
Objectivity in feedback
Participatory Approach
Innovative
Limited assistance provided in achieving key DLIs such as International accreditation and sustainability
Additional & Frequent physical interactions with the experts.
Adequate prior notice before experts' visit
Make room for language disparity